## SLAs & KPIs
Performance Category | SLA Name | Description | Applicable Level | Expected | Min/Max
Quality | BAT Defect Leakage | % of valid defects found in UAT not caught in QA | Release | 2% | ≤5%
Quality | Prod defect leakage – Sev1 & 2 | % of defects leaked to PROD (Sev 1 & 2) per project | Release | 2% | ≤5%
Quality | Prod defect leakage – Sev3 & above | % of defects leaked to PROD (Sev 3 & above) per project | Release | 2% | ≤5%
Quality | Invalid Rejected Defects | Percentage of defects that were found invalid / rejected. | Release | 5% | ≤7%
Efficiency | Test Execution Rate | % increase in net savings from new automation (excl. existing cases) | Release | 95% | 90%
Timelines | Schedule Slippage | Percentage deviation in schedule for a project. Notes: Only applicable to the test schedule not overall project schedule | Release | 95% | ≥90%
Performance Category | KPI Name | Description | Applicable Level | Expected | Min/Max
Quality | %Automation Coverage - E2E | % of E2E scenarios automated per project | Release | 80% | ≥70%
Quality | %Automation Coverage - SIT | % of SIT scenarios automated per project | Release | 80% | ≥70%
Quality | %Automation Coverage - Regression | % of Regression scenarios automated per project | Release | 80% | ≥70%

## SLA-BAT Defect Leakage
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | BAT Sev1+2 Defects | BAT Sev1+2 Defects (Leaked) | Prod Sev1+2 Leakage % | Expected | Min/Max | SLA Met | Start Date | Go-Live Date
Info SCL | Account - Country Specific Information | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Account - Credit Check | IS-012 | Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
DP | Account Management | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
Info SCL | Account Search/MCS | IS-010 | Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP | Activity Management (Tasks/Events/Chatter) | DP-017 | DP Release 17 | Spain | SIT | 96 | 0 | 0 | 0% | 0% | Yes | 2025-05-24 | 2025-06-26
DP | Agreement Management | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL | App20 & inFO | IS-020 | Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL | Assignment Management | IS-006 | Info SCL Release 6 | Germany | UAT | 100 | 1 | 0.99 | 0% | 0% | No | 2025-03-08 | 2025-04-01
Info SCL | Business Proposal - Approval Process | IS-004 | Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP | Business Proposal Management | DP-015 | DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
DP | Call List Management / 6x6 | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Campaign Management | IS-002 | Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
Info SCL | Candidate Onboarding | IS-018 | Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
DP | Career Assistant & inFO | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL | Case Management | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Closing Report Management | DP-023 | DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP | Connect (Screening & Qualification) & inFO | DP-013 | DP Release 13 | Spain | SIT | 20 | 0 | 0 | 0% | 0% | Yes | 2025-04-26 | 2025-05-22
DP | Connect (Sourcing) & inFO | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL | Contact - Candidate Consent (GDPR) | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
DP | Contact - Candidate Management | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP | Contact - Candidate Skill Management | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP | Contact - Candidate Unavailability | DP-023 | DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP | Contact - Client Consent (GDPR) | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP | Contact - Client Management | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Employee Management | IS-010 | Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP | Job - Applicant management (convert/reject) | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Job - ATS Mass Actions | IS-018 | Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
Info SCL | Job - ATS Stages | IS-004 | Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP | Job - Search Job | DP-009 | DP Release 9 | Spain | SIT | 102 | 0 | 0 | 0% | 0% | Yes | 2025-03-29 | 2025-05-04
DP | Job - Skill Management | DP-011 | DP Release 11 | Spain | Regression | 110 | 0 | 0 | 0% | 0% | Yes | 2025-04-12 | 2025-05-12
Info SCL | Job - Warranty Management | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Job Create/Update | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Job Management & Posting | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Job Match | DP-003 | DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
DP | Job Parser | DP-015 | DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL | Job Posting | IS-014 | Info SCL Release 14 | Germany | UAT | 89 | 1 | 1.11 | 0% | 0% | No | 2025-05-03 | 2025-06-04
Info SCL | Journey Management | IS-020 | Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL | Lead Management | IS-020 | Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
DP | Office - Portfolio Management/L100 | DP-003 | DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
Info SCL | Office Account - Market Player Management | IS-002 | Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP | Opportunity - Approval Process | DP-023 | DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
Info SCL | Opportunity Management | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Planbition | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Pre-contract | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Pre-Contract Management | DP-015 | DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL | Profile of Interest | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Quick apply | IS-012 | Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
Info SCL | Report and Dashboard | IS-002 | Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP | Resume Parser | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP | rNPS | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14

## SLA-Prod defect leakage – Sev12
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | BAT Sev1+2 Defects | Prod Sev1+2 Defects (Leaked) | Prod Sev1+2 Leakage % | Expected | Min/Max | SLA Met | Start Date | Go-Live Date
Info SCL | Account - Country Specific Information | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Account - Credit Check | IS-012 | Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
DP | Account Management | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
Info SCL | Account Search/MCS | IS-010 | Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP | Activity Management (Tasks/Events/Chatter) | DP-017 | DP Release 17 | Spain | SIT | 96 | 0 | 0 | 0% | 0% | Yes | 2025-05-24 | 2025-06-26
DP | Agreement Management | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL | App20 & inFO | IS-020 | Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL | Assignment Management | IS-006 | Info SCL Release 6 | Germany | UAT | 100 | 1 | 0.99 | 0% | 0% | No | 2025-03-08 | 2025-04-01
Info SCL | Business Proposal - Approval Process | IS-004 | Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP | Business Proposal Management | DP-015 | DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
DP | Call List Management / 6x6 | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Campaign Management | IS-002 | Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
Info SCL | Candidate Onboarding | IS-018 | Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
DP | Career Assistant & inFO | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL | Case Management | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Closing Report Management | DP-023 | DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP | Connect (Screening & Qualification) & inFO | DP-013 | DP Release 13 | Spain | SIT | 20 | 0 | 0 | 0% | 0% | Yes | 2025-04-26 | 2025-05-22
DP | Connect (Sourcing) & inFO | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL | Contact - Candidate Consent (GDPR) | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
DP | Contact - Candidate Management | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP | Contact - Candidate Skill Management | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP | Contact - Candidate Unavailability | DP-023 | DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP | Contact - Client Consent (GDPR) | DP-019 | DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP | Contact - Client Management | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Employee Management | IS-010 | Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP | Job - Applicant management (convert/reject) | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Job - ATS Mass Actions | IS-018 | Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
Info SCL | Job - ATS Stages | IS-004 | Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP | Job - Search Job | DP-009 | DP Release 9 | Spain | SIT | 102 | 0 | 0 | 0% | 0% | Yes | 2025-03-29 | 2025-05-04
DP | Job - Skill Management | DP-011 | DP Release 11 | Spain | Regression | 110 | 0 | 0 | 0% | 0% | Yes | 2025-04-12 | 2025-05-12
Info SCL | Job - Warranty Management | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Job Create/Update | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Job Management & Posting | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Job Match | DP-003 | DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
DP | Job Parser | DP-015 | DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL | Job Posting | IS-014 | Info SCL Release 14 | Germany | UAT | 89 | 1 | 1.11 | 0% | 0% | No | 2025-05-03 | 2025-06-04
Info SCL | Journey Management | IS-020 | Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL | Lead Management | IS-020 | Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
DP | Office - Portfolio Management/L100 | DP-003 | DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
Info SCL | Office Account - Market Player Management | IS-002 | Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP | Opportunity - Approval Process | DP-023 | DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
Info SCL | Opportunity Management | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Planbition | DP-001 | DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL | Pre-contract | IS-016 | Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP | Pre-Contract Management | DP-015 | DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL | Profile of Interest | IS-008 | Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL | Quick apply | IS-012 | Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
Info SCL | Report and Dashboard | IS-002 | Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP | Resume Parser | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP | rNPS | DP-021 | DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14

## SLA-Prod defect leakage – Sev3
Project Name | Country | Testing Phase | BAT Sev3 Defects | Prod Sev3 Defects (Leaked) | Prod Sev3 Leakage % | Expected | Min/Max | SLA Met | Start Date | Go-Live Date
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP Release 17 | Spain | SIT | 96 | 0 | 0 | 0% | 0% | Yes | 2025-05-24 | 2025-06-26
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL Release 6 | Germany | UAT | 100 | 1 | 0.99 | 0% | 0% | No | 2025-03-08 | 2025-04-01
Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP Release 13 | Spain | SIT | 20 | 0 | 0 | 0% | 0% | Yes | 2025-04-26 | 2025-05-22
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP Release 9 | Spain | SIT | 102 | 0 | 0 | 0% | 0% | Yes | 2025-03-29 | 2025-05-04
DP Release 11 | Spain | Regression | 110 | 0 | 0 | 0% | 0% | Yes | 2025-04-12 | 2025-05-12
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL Release 14 | Germany | UAT | 89 | 1 | 1.11 | 0% | 0% | No | 2025-05-03 | 2025-06-04
Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14

## SLA-Invalid_Rejected_Defects
Project Name | Country | Testing Phase | Invalid SIT Defects | Invalid Reg Defects (Leaked) | Invalid Defects % | Expected | Min/Max | SLA Met | Start Date | Go-Live Date
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP Release 17 | Spain | SIT | 96 | 0 | 0 | 0% | 0% | Yes | 2025-05-24 | 2025-06-26
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL Release 6 | Germany | UAT | 100 | 1 | 0.99 | 0% | 0% | No | 2025-03-08 | 2025-04-01
Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP Release 13 | Spain | SIT | 20 | 0 | 0 | 0% | 0% | Yes | 2025-04-26 | 2025-05-22
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
DP Release 19 | US | Regression | 110 | 1 | 0.9 | 0% | 0% | No | 2025-06-07 | 2025-06-28
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 10 | Germany | UAT | 26 | 0 | 0 | 0% | 0% | Yes | 2025-04-05 | 2025-05-16
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 18 | US | UAT | 45 | 1 | 2.17 | 0% | 0% | No | 2025-05-31 | 2025-06-21
Info SCL Release 4 | Germany | E2E | 118 | 0 | 0 | 0% | 0% | Yes | 2025-02-22 | 2025-03-31
DP Release 9 | Spain | SIT | 102 | 0 | 0 | 0% | 0% | Yes | 2025-03-29 | 2025-05-04
DP Release 11 | Spain | Regression | 110 | 0 | 0 | 0% | 0% | Yes | 2025-04-12 | 2025-05-12
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL Release 14 | Germany | UAT | 89 | 1 | 1.11 | 0% | 0% | No | 2025-05-03 | 2025-06-04
Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
Info SCL Release 20 | US | E2E | 83 | 0 | 0 | 0% | 0% | Yes | 2025-06-14 | 2025-07-20
DP Release 3 | Spain | Regression | 70 | 0 | 0 | 0% | 0% | Yes | 2025-02-15 | 2025-03-20
Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP Release 23 | Italy | Regression | 28 | 1 | 3.45 | 0% | 0% | No | 2025-07-05 | 2025-08-13
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 1 | Spain | SIT | 61 | 0 | 0 | 0% | 0% | Yes | 2025-02-01 | 2025-02-27
Info SCL Release 16 | US | E2E | 119 | 0 | 0 | 0% | 0% | Yes | 2025-05-17 | 2025-06-11
DP Release 15 | Spain | Regression | 77 | 0 | 0 | 0% | 0% | Yes | 2025-05-10 | 2025-06-22
Info SCL Release 8 | Germany | E2E | 32 | 1 | 3.03 | 0% | 0% | No | 2025-03-22 | 2025-04-28
Info SCL Release 12 | Germany | E2E | 100 | 0 | 0 | 0% | 0% | Yes | 2025-04-19 | 2025-05-23
Info SCL Release 2 | Germany | UAT | 38 | 1 | 2.56 | 0% | 0% | No | 2025-02-08 | 2025-03-07
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14
DP Release 21 | Italy | SIT | 73 | 0 | 0 | 0% | 0% | Yes | 2025-06-21 | 2025-07-14

## SLA_Test_Execution_Rate
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | Planned Start | Planned End | Actual Start | Actual End | Schedule Variance (days) | Planned Test Cases | Executed On-time | Executed Late | On-time Execution % | Expected | Min/Max | SLA Met
Info SCL | Account - Country Specific Information | IS-015 | Info SCL Release 15 | Germany | E2E | 2025-04-06 | 2025-04-20 | 2025-04-06 | 2025-04-19 | -1 | 341 | 339 | 2 | 99.41 | 100% | ≥99% | Yes
Info SCL | Account - Credit Check | IS-005 | Info SCL Release 5 | Germany | E2E | 2025-02-05 | 2025-03-02 | 2025-02-07 | 2025-03-01 | -1 | 1066 | 1059 | 7 | 99.34 | 100% | ≥99% | Yes
Info SCL | Account Management | IS-013 | Info SCL Release 13 | Italy | SIT | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
Info SCL | Account Search/MCS | IS-023 | Info SCL Release 23 | Germany | UAT | 2025-05-24 | 2025-06-21 | 2025-05-24 | 2025-06-18 | -3 | 1411 | 1409 | 2 | 99.86 | 100% | ≥99% | Yes
Info SCL | Activity Management (Tasks/Events/Chatter) | IS-009 | Info SCL Release 9 | Spain | SIT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
DP | Agreement Management | DP-008 | DP Release 8 | US | Regression | 2025-02-23 | 2025-03-15 | 2025-02-25 | 2025-03-13 | -2 | 1500 | 1487 | 13 | 99.13 | 100% | ≥99% | Yes
DP | App20 & inFO | DP-024 | DP Release 24 | US | E2E | 2025-05-30 | 2025-06-10 | 2025-05-30 | 2025-06-11 | 1 | 493 | 478 | 15 | 96.96 | 100% | ≥99% | No
Info SCL | Assignment Management | IS-009 | Info SCL Release 9 | Germany | UAT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
DP | Business Proposal - Approval Process | DP-022 | DP Release 22 | Germany | E2E | 2025-05-18 | 2025-06-18 | 2025-05-19 | 2025-06-19 | 1 | 871 | 868 | 3 | 99.66 | 100% | ≥99% | Yes
Info SCL | Business Proposal Management | IS-019 | Info SCL Release 19 | Spain | Regression | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
Info SCL | Call List Management / 6x6 | IS-023 | Info SCL Release 23 | Spain | SIT | 2025-05-24 | 2025-06-21 | 2025-05-24 | 2025-06-18 | -3 | 1411 | 1409 | 2 | 99.86 | 100% | ≥99% | Yes
DP | Campaign Management | DP-024 | DP Release 24 | Germany | UAT | 2025-05-30 | 2025-06-10 | 2025-05-30 | 2025-06-11 | 1 | 493 | 478 | 15 | 96.96 | 100% | ≥99% | No
DP | Candidate Onboarding | DP-020 | DP Release 20 | US | UAT | 2025-05-06 | 2025-05-29 | 2025-05-06 | 2025-05-31 | 2 | 1408 | 1369 | 39 | 97.23 | 100% | ≥99% | No
Info SCL | Career Assistant & inFO | IS-013 | Info SCL Release 13 | US | Regression | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
DP | Case Management | DP-006 | DP Release 6 | US | E2E | 2025-02-11 | 2025-02-21 | 2025-02-12 | 2025-02-19 | -2 | 156 | 156 | 0 | 100 | 100% | ≥99% | Yes
Info SCL | Closing Report Management | IS-017 | Info SCL Release 17 | Italy | Regression | 2025-04-18 | 2025-05-15 | 2025-04-18 | 2025-05-19 | 4 | 944 | 931 | 13 | 98.62 | 100% | ≥99% | No
DP | Connect (Screening & Qualification) & inFO | DP-024 | DP Release 24 | Spain | SIT | 2025-05-30 | 2025-06-10 | 2025-05-30 | 2025-06-11 | 1 | 493 | 478 | 15 | 96.96 | 100% | ≥99% | No
Info SCL | Connect (Sourcing) & inFO | IS-017 | Info SCL Release 17 | US | Regression | 2025-04-18 | 2025-05-15 | 2025-04-18 | 2025-05-19 | 4 | 944 | 931 | 13 | 98.62 | 100% | ≥99% | No
DP | Contact - Candidate Consent (GDPR) | DP-016 | DP Release 16 | Germany | E2E | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
Info SCL | Contact - Candidate Management | IS-013 | Info SCL Release 13 | Italy | SIT | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
DP | Contact - Candidate Skill Management | DP-014 | DP Release 14 | US | Regression | 2025-03-31 | 2025-04-19 | 2025-04-02 | 2025-04-18 | -1 | 1058 | 1057 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Contact - Candidate Unavailability | DP-006 | DP Release 6 | Italy | Regression | 2025-02-11 | 2025-02-21 | 2025-02-12 | 2025-02-19 | -2 | 156 | 156 | 0 | 100 | 100% | ≥99% | Yes
DP | Contact - Client Consent (GDPR) | DP-010 | DP Release 10 | US | Regression | 2025-03-07 | 2025-03-30 | 2025-03-09 | 2025-04-03 | 4 | 592 | 577 | 15 | 97.47 | 100% | ≥99% | No
DP | Contact - Client Management | DP-020 | DP Release 20 | Spain | SIT | 2025-05-06 | 2025-05-29 | 2025-05-06 | 2025-05-31 | 2 | 1408 | 1369 | 39 | 97.23 | 100% | ≥99% | No
Info SCL | Employee Management | IS-017 | Info SCL Release 17 | Germany | UAT | 2025-04-18 | 2025-05-15 | 2025-04-18 | 2025-05-19 | 4 | 944 | 931 | 13 | 98.62 | 100% | ≥99% | No
DP | Job - Applicant management (convert/reject) | DP-020 | DP Release 20 | Spain | SIT | 2025-05-06 | 2025-05-29 | 2025-05-06 | 2025-05-31 | 2 | 1408 | 1369 | 39 | 97.23 | 100% | ≥99% | No
Info SCL | Job - ATS Mass Actions | IS-011 | Info SCL Release 11 | US | UAT | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
Info SCL | Job - ATS Stages | IS-019 | Info SCL Release 19 | Germany | E2E | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
DP | Job - Search Job | DP-022 | DP Release 22 | Spain | SIT | 2025-05-18 | 2025-06-18 | 2025-05-19 | 2025-06-19 | 1 | 871 | 868 | 3 | 99.66 | 100% | ≥99% | Yes
Info SCL | Job - Skill Management | IS-011 | Info SCL Release 11 | Spain | Regression | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Job - Warranty Management | DP-016 | DP Release 16 | Germany | E2E | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
DP | Job Create/Update | DP-018 | DP Release 18 | Germany | E2E | 2025-04-24 | 2025-05-03 | 2025-04-26 | 2025-05-03 | 0 | 518 | 515 | 3 | 99.42 | 100% | ≥99% | Yes
DP | Job Management & Posting | DP-014 | DP Release 14 | US | E2E | 2025-03-31 | 2025-04-19 | 2025-04-02 | 2025-04-18 | -1 | 1058 | 1057 | 1 | 99.91 | 100% | ≥99% | Yes
Info SCL | Job Match | IS-011 | Info SCL Release 11 | Spain | Regression | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Job Parser | DP-016 | DP Release 16 | Spain | Regression | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
Info SCL | Job Posting | IS-009 | Info SCL Release 9 | Germany | UAT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
Info SCL | Journey Management | IS-011 | Info SCL Release 11 | US | E2E | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Lead Management | DP-016 | DP Release 16 | US | E2E | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
DP | Office - Portfolio Management/L100 | DP-016 | DP Release 16 | Spain | Regression | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
DP | Office Account - Market Player Management | DP-012 | DP Release 12 | Germany | UAT | 2025-03-19 | 2025-03-30 | 2025-03-19 | 2025-03-31 | 1 | 403 | 402 | 1 | 99.75 | 100% | ≥99% | Yes
Info SCL | Opportunity - Approval Process | IS-015 | Info SCL Release 15 | Italy | Regression | 2025-04-06 | 2025-04-20 | 2025-04-06 | 2025-04-19 | -1 | 341 | 339 | 2 | 99.41 | 100% | ≥99% | Yes
Info SCL | Opportunity Management | IS-013 | Info SCL Release 13 | US | E2E | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
Info SCL | Planbition | IS-003 | Info SCL Release 3 | Spain | SIT | 2025-01-24 | 2025-02-05 | 2025-01-26 | 2025-02-06 | 1 | 324 | 322 | 2 | 99.38 | 100% | ≥99% | Yes
DP | Pre-contract | DP-014 | DP Release 14 | US | E2E | 2025-03-31 | 2025-04-19 | 2025-04-02 | 2025-04-18 | -1 | 1058 | 1057 | 1 | 99.91 | 100% | ≥99% | Yes
Info SCL | Pre-Contract Management | IS-009 | Info SCL Release 9 | Spain | Regression | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
Info SCL | Profile of Interest | IS-005 | Info SCL Release 5 | Germany | E2E | 2025-02-05 | 2025-03-02 | 2025-02-07 | 2025-03-01 | -1 | 1066 | 1059 | 7 | 99.34 | 100% | ≥99% | Yes
Info SCL | Quick apply | IS-019 | Info SCL Release 19 | Germany | E2E | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
Info SCL | Report and Dashboard | IS-013 | Info SCL Release 13 | Germany | UAT | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
Info SCL | Resume Parser | IS-019 | Info SCL Release 19 | Italy | SIT | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
Info SCL | rNPS | IS-009 | Info SCL Release 9 | Italy | SIT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes

## SLA- Schedule Slippage
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | Planned Start | Planned End | Actual Start | Actual End | Schedule Variance (days) | Planned Test Cases | Executed On-time | Executed Late | On-time Execution % | Expected | Min/Max | SLA Met
Info SCL | Account - Country Specific Information | IS-015 | Info SCL Release 15 | Germany | E2E | 2025-04-06 | 2025-04-20 | 2025-04-06 | 2025-04-19 | -1 | 341 | 339 | 2 | 99.41 | 100% | ≥99% | Yes
Info SCL | Account - Credit Check | IS-005 | Info SCL Release 5 | Germany | E2E | 2025-02-05 | 2025-03-02 | 2025-02-07 | 2025-03-01 | -1 | 1066 | 1059 | 7 | 99.34 | 100% | ≥99% | Yes
Info SCL | Account Management | IS-013 | Info SCL Release 13 | Italy | SIT | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
Info SCL | Account Search/MCS | IS-023 | Info SCL Release 23 | Germany | UAT | 2025-05-24 | 2025-06-21 | 2025-05-24 | 2025-06-18 | -3 | 1411 | 1409 | 2 | 99.86 | 100% | ≥99% | Yes
Info SCL | Activity Management (Tasks/Events/Chatter) | IS-009 | Info SCL Release 9 | Spain | SIT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
DP | Agreement Management | DP-008 | DP Release 8 | US | Regression | 2025-02-23 | 2025-03-15 | 2025-02-25 | 2025-03-13 | -2 | 1500 | 1487 | 13 | 99.13 | 100% | ≥99% | Yes
DP | App20 & inFO | DP-024 | DP Release 24 | US | E2E | 2025-05-30 | 2025-06-10 | 2025-05-30 | 2025-06-11 | 1 | 493 | 478 | 15 | 96.96 | 100% | ≥99% | No
Info SCL | Assignment Management | IS-009 | Info SCL Release 9 | Germany | UAT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
DP | Business Proposal - Approval Process | DP-022 | DP Release 22 | Germany | E2E | 2025-05-18 | 2025-06-18 | 2025-05-19 | 2025-06-19 | 1 | 871 | 868 | 3 | 99.66 | 100% | ≥99% | Yes
Info SCL | Business Proposal Management | IS-019 | Info SCL Release 19 | Spain | Regression | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
Info SCL | Call List Management / 6x6 | IS-023 | Info SCL Release 23 | Spain | SIT | 2025-05-24 | 2025-06-21 | 2025-05-24 | 2025-06-18 | -3 | 1411 | 1409 | 2 | 99.86 | 100% | ≥99% | Yes
DP | Campaign Management | DP-024 | DP Release 24 | Germany | UAT | 2025-05-30 | 2025-06-10 | 2025-05-30 | 2025-06-11 | 1 | 493 | 478 | 15 | 96.96 | 100% | ≥99% | No
DP | Candidate Onboarding | DP-020 | DP Release 20 | US | UAT | 2025-05-06 | 2025-05-29 | 2025-05-06 | 2025-05-31 | 2 | 1408 | 1369 | 39 | 97.23 | 100% | ≥99% | No
Info SCL | Career Assistant & inFO | IS-013 | Info SCL Release 13 | US | Regression | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
DP | Case Management | DP-006 | DP Release 6 | US | E2E | 2025-02-11 | 2025-02-21 | 2025-02-12 | 2025-02-19 | -2 | 156 | 156 | 0 | 100 | 100% | ≥99% | Yes
Info SCL | Closing Report Management | IS-017 | Info SCL Release 17 | Italy | Regression | 2025-04-18 | 2025-05-15 | 2025-04-18 | 2025-05-19 | 4 | 944 | 931 | 13 | 98.62 | 100% | ≥99% | No
DP | Connect (Screening & Qualification) & inFO | DP-024 | DP Release 24 | Spain | SIT | 2025-05-30 | 2025-06-10 | 2025-05-30 | 2025-06-11 | 1 | 493 | 478 | 15 | 96.96 | 100% | ≥99% | No
Info SCL | Connect (Sourcing) & inFO | IS-017 | Info SCL Release 17 | US | Regression | 2025-04-18 | 2025-05-15 | 2025-04-18 | 2025-05-19 | 4 | 944 | 931 | 13 | 98.62 | 100% | ≥99% | No
DP | Contact - Candidate Consent (GDPR) | DP-016 | DP Release 16 | Germany | E2E | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
Info SCL | Contact - Candidate Management | IS-013 | Info SCL Release 13 | Italy | SIT | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
DP | Contact - Candidate Skill Management | DP-014 | DP Release 14 | US | Regression | 2025-03-31 | 2025-04-19 | 2025-04-02 | 2025-04-18 | -1 | 1058 | 1057 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Contact - Candidate Unavailability | DP-006 | DP Release 6 | Italy | Regression | 2025-02-11 | 2025-02-21 | 2025-02-12 | 2025-02-19 | -2 | 156 | 156 | 0 | 100 | 100% | ≥99% | Yes
DP | Contact - Client Consent (GDPR) | DP-010 | DP Release 10 | US | Regression | 2025-03-07 | 2025-03-30 | 2025-03-09 | 2025-04-03 | 4 | 592 | 577 | 15 | 97.47 | 100% | ≥99% | No
DP | Contact - Client Management | DP-020 | DP Release 20 | Spain | SIT | 2025-05-06 | 2025-05-29 | 2025-05-06 | 2025-05-31 | 2 | 1408 | 1369 | 39 | 97.23 | 100% | ≥99% | No
Info SCL | Employee Management | IS-017 | Info SCL Release 17 | Germany | UAT | 2025-04-18 | 2025-05-15 | 2025-04-18 | 2025-05-19 | 4 | 944 | 931 | 13 | 98.62 | 100% | ≥99% | No
DP | Job - Applicant management (convert/reject) | DP-020 | DP Release 20 | Spain | SIT | 2025-05-06 | 2025-05-29 | 2025-05-06 | 2025-05-31 | 2 | 1408 | 1369 | 39 | 97.23 | 100% | ≥99% | No
Info SCL | Job - ATS Mass Actions | IS-011 | Info SCL Release 11 | US | UAT | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
Info SCL | Job - ATS Stages | IS-019 | Info SCL Release 19 | Germany | E2E | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
DP | Job - Search Job | DP-022 | DP Release 22 | Spain | SIT | 2025-05-18 | 2025-06-18 | 2025-05-19 | 2025-06-19 | 1 | 871 | 868 | 3 | 99.66 | 100% | ≥99% | Yes
Info SCL | Job - Skill Management | IS-011 | Info SCL Release 11 | Spain | Regression | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Job - Warranty Management | DP-016 | DP Release 16 | Germany | E2E | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
DP | Job Create/Update | DP-018 | DP Release 18 | Germany | E2E | 2025-04-24 | 2025-05-03 | 2025-04-26 | 2025-05-03 | 0 | 518 | 515 | 3 | 99.42 | 100% | ≥99% | Yes
DP | Job Management & Posting | DP-014 | DP Release 14 | US | E2E | 2025-03-31 | 2025-04-19 | 2025-04-02 | 2025-04-18 | -1 | 1058 | 1057 | 1 | 99.91 | 100% | ≥99% | Yes
Info SCL | Job Match | IS-011 | Info SCL Release 11 | Spain | Regression | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Job Parser | DP-016 | DP Release 16 | Spain | Regression | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
Info SCL | Job Posting | IS-009 | Info SCL Release 9 | Germany | UAT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
Info SCL | Journey Management | IS-011 | Info SCL Release 11 | US | E2E | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-04-03 | -2 | 1062 | 1061 | 1 | 99.91 | 100% | ≥99% | Yes
DP | Lead Management | DP-016 | DP Release 16 | US | E2E | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
DP | Office - Portfolio Management/L100 | DP-016 | DP Release 16 | Spain | Regression | 2025-04-12 | 2025-05-05 | 2025-04-13 | 2025-05-07 | 2 | 1074 | 1038 | 36 | 96.65 | 100% | ≥99% | No
DP | Office Account - Market Player Management | DP-012 | DP Release 12 | Germany | UAT | 2025-03-19 | 2025-03-30 | 2025-03-19 | 2025-03-31 | 1 | 403 | 402 | 1 | 99.75 | 100% | ≥99% | Yes
Info SCL | Opportunity - Approval Process | IS-015 | Info SCL Release 15 | Italy | Regression | 2025-04-06 | 2025-04-20 | 2025-04-06 | 2025-04-19 | -1 | 341 | 339 | 2 | 99.41 | 100% | ≥99% | Yes
Info SCL | Opportunity Management | IS-013 | Info SCL Release 13 | US | E2E | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
Info SCL | Planbition | IS-003 | Info SCL Release 3 | Spain | SIT | 2025-01-24 | 2025-02-05 | 2025-01-26 | 2025-02-06 | 1 | 324 | 322 | 2 | 99.38 | 100% | ≥99% | Yes
DP | Pre-contract | DP-014 | DP Release 14 | US | E2E | 2025-03-31 | 2025-04-19 | 2025-04-02 | 2025-04-18 | -1 | 1058 | 1057 | 1 | 99.91 | 100% | ≥99% | Yes
Info SCL | Pre-Contract Management | IS-009 | Info SCL Release 9 | Spain | Regression | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes
Info SCL | Profile of Interest | IS-005 | Info SCL Release 5 | Germany | E2E | 2025-02-05 | 2025-03-02 | 2025-02-07 | 2025-03-01 | -1 | 1066 | 1059 | 7 | 99.34 | 100% | ≥99% | Yes
Info SCL | Quick apply | IS-019 | Info SCL Release 19 | Germany | E2E | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
Info SCL | Report and Dashboard | IS-013 | Info SCL Release 13 | Germany | UAT | 2025-03-25 | 2025-04-08 | 2025-03-25 | 2025-04-07 | -1 | 1379 | 1366 | 13 | 99.06 | 100% | ≥99% | Yes
Info SCL | Resume Parser | IS-019 | Info SCL Release 19 | Italy | SIT | 2025-04-30 | 2025-05-17 | 2025-05-01 | 2025-05-17 | 0 | 1665 | 1649 | 16 | 99.04 | 100% | ≥99% | Yes
Info SCL | rNPS | IS-009 | Info SCL Release 9 | Italy | SIT | 2025-03-01 | 2025-03-13 | 2025-03-02 | 2025-03-13 | 0 | 215 | 215 | 0 | 100 | 100% | ≥99% | Yes

## KPI-%Automation Coverage - E2E
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | Total E2E Scenarios | Automated Scenarios | % E2E Scenarios Automated | Expected | Min/Max | KPI Met | Automation Start | KPI Review Date
Info SCL | Account - Country Specific Information | IS-015 | Info SCL Release 15 | Germany | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
Info SCL | Account - Credit Check | IS-005 | Info SCL Release 5 | Germany | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
Info SCL | Account Management | IS-013 | Info SCL Release 13 | Italy | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
Info SCL | Account Search/MCS | IS-023 | Info SCL Release 23 | Germany | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
Info SCL | Activity Management (Tasks/Events/Chatter) | IS-009 | Info SCL Release 9 | Spain | Regression | 174 | 167 | 95.98 | 100% | ≥99% | No | 2025-07-20 | 2025-12-28
DP | Agreement Management | DP-008 | DP Release 8 | US | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
DP | App20 & inFO | DP-024 | DP Release 24 | US | E2E | 102 | 102 | 100 | 100% | ≥99% | Yes | 2025-05-25 | 2025-11-20
Info SCL | Assignment Management | IS-009 | Info SCL Release 9 | Germany | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
DP | Business Proposal - Approval Process | DP-022 | DP Release 22 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Business Proposal Management | IS-019 | Info SCL Release 19 | Spain | Regression | 75 | 74 | 98.67 | 100% | ≥99% | No | 2025-04-15 | 2025-10-10
Info SCL | Call List Management / 6x6 | IS-023 | Info SCL Release 23 | Spain | SIT | 136 | 136 | 100 | 100% | ≥99% | Yes | 2025-02-26 | 2025-08-07
DP | Campaign Management | DP-024 | DP Release 24 | Germany | SIT | 66 | 63 | 95.45 | 100% | ≥99% | No | 2025-06-02 | 2025-11-20
DP | Candidate Onboarding | DP-020 | DP Release 20 | US | E2E | 100 | 100 | 100 | 100% | ≥99% | Yes | 2025-04-23 | 2025-10-25
Info SCL | Career Assistant & inFO | IS-013 | Info SCL Release 13 | US | E2E | 102 | 102 | 100 | 100% | ≥99% | Yes | 2025-05-25 | 2025-11-20
DP | Case Management | DP-006 | DP Release 6 | US | UAT | 172 | 171 | 99.42 | 100% | ≥99% | Yes | 2025-07-12 | 2025-12-20
Info SCL | Closing Report Management | IS-017 | Info SCL Release 17 | Italy | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
DP | Connect (Screening & Qualification) & inFO | DP-024 | DP Release 24 | Spain | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
Info SCL | Connect (Sourcing) & inFO | IS-017 | Info SCL Release 17 | US | Regression | 75 | 74 | 98.67 | 100% | ≥99% | No | 2025-04-15 | 2025-10-10
DP | Contact - Candidate Consent (GDPR) | DP-016 | DP Release 16 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Contact - Candidate Management | IS-013 | Info SCL Release 13 | Italy | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
DP | Contact - Candidate Skill Management | DP-014 | DP Release 14 | US | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
DP | Contact - Candidate Unavailability | DP-006 | DP Release 6 | Italy | E2E | 100 | 100 | 100 | 100% | ≥99% | Yes | 2025-04-23 | 2025-10-25
DP | Contact - Client Consent (GDPR) | DP-010 | DP Release 10 | US | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
DP | Contact - Client Management | DP-020 | DP Release 20 | Spain | SIT | 79 | 77 | 97.47 | 100% | ≥99% | No | 2025-01-25 | 2025-07-22
Info SCL | Employee Management | IS-017 | Info SCL Release 17 | Germany | Regression | 174 | 171 | 98.28 | 100% | ≥99% | No | 2025-06-18 | 2025-12-09
DP | Job - Applicant management (convert/reject) | DP-020 | DP Release 20 | Spain | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Job - ATS Mass Actions | IS-011 | Info SCL Release 11 | US | Regression | 141 | 140 | 99.29 | 100% | ≥99% | Yes | 2025-02-10 | 2025-08-09
Info SCL | Job - ATS Stages | IS-019 | Info SCL Release 19 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
DP | Job - Search Job | DP-022 | DP Release 22 | Spain | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
Info SCL | Job - Skill Management | IS-011 | Info SCL Release 11 | Spain | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
DP | Job - Warranty Management | DP-016 | DP Release 16 | Germany | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
DP | Job Create/Update | DP-018 | DP Release 18 | Germany | SIT | 79 | 77 | 97.47 | 100% | ≥99% | No | 2025-01-25 | 2025-07-22
DP | Job Management & Posting | DP-014 | DP Release 14 | US | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
Info SCL | Job Match | IS-011 | Info SCL Release 11 | Spain | Regression | 174 | 171 | 98.28 | 100% | ≥99% | No | 2025-06-18 | 2025-12-09
DP | Job Parser | DP-016 | DP Release 16 | Spain | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
Info SCL | Job Posting | IS-009 | Info SCL Release 9 | Germany | UAT | 193 | 193 | 100 | 100% | ≥99% | Yes | 2025-04-07 | 2025-10-03
Info SCL | Journey Management | IS-011 | Info SCL Release 11 | US | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
DP | Lead Management | DP-016 | DP Release 16 | US | Regression | 187 | 184 | 98.4 | 100% | ≥99% | No | 2025-05-17 | 2025-11-17
DP | Office - Portfolio Management/L100 | DP-016 | DP Release 16 | Spain | SIT | 136 | 136 | 100 | 100% | ≥99% | Yes | 2025-02-26 | 2025-08-07
DP | Office Account - Market Player Management | DP-012 | DP Release 12 | Germany | SIT | 66 | 63 | 95.45 | 100% | ≥99% | No | 2025-06-02 | 2025-11-20
Info SCL | Opportunity - Approval Process | IS-015 | Info SCL Release 15 | Italy | SIT | 197 | 196 | 99.49 | 100% | ≥99% | Yes | 2025-07-04 | 2025-12-28
Info SCL | Opportunity Management | IS-013 | Info SCL Release 13 | US | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
Info SCL | Planbition | IS-003 | Info SCL Release 3 | Spain | SIT | 108 | 108 | 100 | 100% | ≥99% | Yes | 2025-03-30 | 2025-09-29
DP | Pre-contract | DP-014 | DP Release 14 | US | UAT | 172 | 171 | 99.42 | 100% | ≥99% | Yes | 2025-07-12 | 2025-12-20
Info SCL | Pre-Contract Management | IS-009 | Info SCL Release 9 | Spain | SIT | 108 | 108 | 100 | 100% | ≥99% | Yes | 2025-03-30 | 2025-09-29
Info SCL | Profile of Interest | IS-005 | Info SCL Release 5 | Germany | Regression | 174 | 167 | 95.98 | 100% | ≥99% | No | 2025-07-20 | 2025-12-28
Info SCL | Quick apply | IS-019 | Info SCL Release 19 | Germany | Regression | 187 | 184 | 98.4 | 100% | ≥99% | No | 2025-05-17 | 2025-11-17
Info SCL | Report and Dashboard | IS-013 | Info SCL Release 13 | Germany | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
Info SCL | Resume Parser | IS-019 | Info SCL Release 19 | Italy | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
Info SCL | rNPS | IS-009 | Info SCL Release 9 | Italy | Regression | 197 | 195 | 98.98 | 100% | ≥99% | No | 2025-03-14 | 2025-08-23

## KPI-%Automation Coverage -SIT
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | Total SIT Scenarios | Automated Scenarios | % SIT Scenarios Automated | Expected | Min/Max | KPI Met | Automation Start | KPI Review Date
Info SCL | Account - Country Specific Information | IS-015 | Info SCL Release 15 | Germany | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
Info SCL | Account - Credit Check | IS-005 | Info SCL Release 5 | Germany | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
Info SCL | Account Management | IS-013 | Info SCL Release 13 | Italy | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
Info SCL | Account Search/MCS | IS-023 | Info SCL Release 23 | Germany | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
Info SCL | Activity Management (Tasks/Events/Chatter) | IS-009 | Info SCL Release 9 | Spain | Regression | 174 | 167 | 95.98 | 100% | ≥99% | No | 2025-07-20 | 2025-12-28
DP | Agreement Management | DP-008 | DP Release 8 | US | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
DP | App20 & inFO | DP-024 | DP Release 24 | US | E2E | 102 | 102 | 100 | 100% | ≥99% | Yes | 2025-05-25 | 2025-11-20
Info SCL | Assignment Management | IS-009 | Info SCL Release 9 | Germany | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
DP | Business Proposal - Approval Process | DP-022 | DP Release 22 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Business Proposal Management | IS-019 | Info SCL Release 19 | Spain | Regression | 75 | 74 | 98.67 | 100% | ≥99% | No | 2025-04-15 | 2025-10-10
Info SCL | Call List Management / 6x6 | IS-023 | Info SCL Release 23 | Spain | SIT | 136 | 136 | 100 | 100% | ≥99% | Yes | 2025-02-26 | 2025-08-07
DP | Campaign Management | DP-024 | DP Release 24 | Germany | SIT | 66 | 63 | 95.45 | 100% | ≥99% | No | 2025-06-02 | 2025-11-20
DP | Candidate Onboarding | DP-020 | DP Release 20 | US | E2E | 100 | 100 | 100 | 100% | ≥99% | Yes | 2025-04-23 | 2025-10-25
Info SCL | Career Assistant & inFO | IS-013 | Info SCL Release 13 | US | E2E | 102 | 102 | 100 | 100% | ≥99% | Yes | 2025-05-25 | 2025-11-20
DP | Case Management | DP-006 | DP Release 6 | US | UAT | 172 | 171 | 99.42 | 100% | ≥99% | Yes | 2025-07-12 | 2025-12-20
Info SCL | Closing Report Management | IS-017 | Info SCL Release 17 | Italy | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
DP | Connect (Screening & Qualification) & inFO | DP-024 | DP Release 24 | Spain | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
Info SCL | Connect (Sourcing) & inFO | IS-017 | Info SCL Release 17 | US | Regression | 75 | 74 | 98.67 | 100% | ≥99% | No | 2025-04-15 | 2025-10-10
DP | Contact - Candidate Consent (GDPR) | DP-016 | DP Release 16 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Contact - Candidate Management | IS-013 | Info SCL Release 13 | Italy | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
DP | Contact - Candidate Skill Management | DP-014 | DP Release 14 | US | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
DP | Contact - Candidate Unavailability | DP-006 | DP Release 6 | Italy | E2E | 100 | 100 | 100 | 100% | ≥99% | Yes | 2025-04-23 | 2025-10-25
DP | Contact - Client Consent (GDPR) | DP-010 | DP Release 10 | US | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
DP | Contact - Client Management | DP-020 | DP Release 20 | Spain | SIT | 79 | 77 | 97.47 | 100% | ≥99% | No | 2025-01-25 | 2025-07-22
Info SCL | Employee Management | IS-017 | Info SCL Release 17 | Germany | Regression | 174 | 171 | 98.28 | 100% | ≥99% | No | 2025-06-18 | 2025-12-09
DP | Job - Applicant management (convert/reject) | DP-020 | DP Release 20 | Spain | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Job - ATS Mass Actions | IS-011 | Info SCL Release 11 | US | Regression | 141 | 140 | 99.29 | 100% | ≥99% | Yes | 2025-02-10 | 2025-08-09
Info SCL | Job - ATS Stages | IS-019 | Info SCL Release 19 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
DP | Job - Search Job | DP-022 | DP Release 22 | Spain | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
Info SCL | Job - Skill Management | IS-011 | Info SCL Release 11 | Spain | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
DP | Job - Warranty Management | DP-016 | DP Release 16 | Germany | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
DP | Job Create/Update | DP-018 | DP Release 18 | Germany | SIT | 79 | 77 | 97.47 | 100% | ≥99% | No | 2025-01-25 | 2025-07-22
DP | Job Management & Posting | DP-014 | DP Release 14 | US | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
Info SCL | Job Match | IS-011 | Info SCL Release 11 | Spain | Regression | 174 | 171 | 98.28 | 100% | ≥99% | No | 2025-06-18 | 2025-12-09
DP | Job Parser | DP-016 | DP Release 16 | Spain | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
Info SCL | Job Posting | IS-009 | Info SCL Release 9 | Germany | UAT | 193 | 193 | 100 | 100% | ≥99% | Yes | 2025-04-07 | 2025-10-03
Info SCL | Journey Management | IS-011 | Info SCL Release 11 | US | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
DP | Lead Management | DP-016 | DP Release 16 | US | Regression | 187 | 184 | 98.4 | 100% | ≥99% | No | 2025-05-17 | 2025-11-17
DP | Office - Portfolio Management/L100 | DP-016 | DP Release 16 | Spain | SIT | 136 | 136 | 100 | 100% | ≥99% | Yes | 2025-02-26 | 2025-08-07
DP | Office Account - Market Player Management | DP-012 | DP Release 12 | Germany | SIT | 66 | 63 | 95.45 | 100% | ≥99% | No | 2025-06-02 | 2025-11-20
Info SCL | Opportunity - Approval Process | IS-015 | Info SCL Release 15 | Italy | SIT | 197 | 196 | 99.49 | 100% | ≥99% | Yes | 2025-07-04 | 2025-12-28
Info SCL | Opportunity Management | IS-013 | Info SCL Release 13 | US | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
Info SCL | Planbition | IS-003 | Info SCL Release 3 | Spain | SIT | 108 | 108 | 100 | 100% | ≥99% | Yes | 2025-03-30 | 2025-09-29
DP | Pre-contract | DP-014 | DP Release 14 | US | UAT | 172 | 171 | 99.42 | 100% | ≥99% | Yes | 2025-07-12 | 2025-12-20
Info SCL | Pre-Contract Management | IS-009 | Info SCL Release 9 | Spain | SIT | 108 | 108 | 100 | 100% | ≥99% | Yes | 2025-03-30 | 2025-09-29
Info SCL | Profile of Interest | IS-005 | Info SCL Release 5 | Germany | Regression | 174 | 167 | 95.98 | 100% | ≥99% | No | 2025-07-20 | 2025-12-28
Info SCL | Quick apply | IS-019 | Info SCL Release 19 | Germany | Regression | 187 | 184 | 98.4 | 100% | ≥99% | No | 2025-05-17 | 2025-11-17
Info SCL | Report and Dashboard | IS-013 | Info SCL Release 13 | Germany | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
Info SCL | Resume Parser | IS-019 | Info SCL Release 19 | Italy | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
Info SCL | rNPS | IS-009 | Info SCL Release 9 | Italy | Regression | 197 | 195 | 98.98 | 100% | ≥99% | No | 2025-03-14 | 2025-08-23

## KPI-%Automation Coverage -Reg
Business Stream | Portfolio | Project ID | Project Name | Country | Testing Phase | Total Reg Scenarios | Automated Scenarios | % Reg Scenarios Automated | Expected | Min/Max | KPI Met | Automation Start | KPI Review Date
Info SCL | Account - Country Specific Information | IS-015 | Info SCL Release 15 | Germany | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
Info SCL | Account - Credit Check | IS-005 | Info SCL Release 5 | Germany | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
Info SCL | Account Management | IS-013 | Info SCL Release 13 | Italy | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
Info SCL | Account Search/MCS | IS-023 | Info SCL Release 23 | Germany | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
Info SCL | Activity Management (Tasks/Events/Chatter) | IS-009 | Info SCL Release 9 | Spain | Regression | 174 | 167 | 95.98 | 100% | ≥99% | No | 2025-07-20 | 2025-12-28
DP | Agreement Management | DP-008 | DP Release 8 | US | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
DP | App20 & inFO | DP-024 | DP Release 24 | US | E2E | 102 | 102 | 100 | 100% | ≥99% | Yes | 2025-05-25 | 2025-11-20
Info SCL | Assignment Management | IS-009 | Info SCL Release 9 | Germany | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
DP | Business Proposal - Approval Process | DP-022 | DP Release 22 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Business Proposal Management | IS-019 | Info SCL Release 19 | Spain | Regression | 75 | 74 | 98.67 | 100% | ≥99% | No | 2025-04-15 | 2025-10-10
Info SCL | Call List Management / 6x6 | IS-023 | Info SCL Release 23 | Spain | SIT | 136 | 136 | 100 | 100% | ≥99% | Yes | 2025-02-26 | 2025-08-07
DP | Campaign Management | DP-024 | DP Release 24 | Germany | SIT | 66 | 63 | 95.45 | 100% | ≥99% | No | 2025-06-02 | 2025-11-20
DP | Candidate Onboarding | DP-020 | DP Release 20 | US | E2E | 100 | 100 | 100 | 100% | ≥99% | Yes | 2025-04-23 | 2025-10-25
Info SCL | Career Assistant & inFO | IS-013 | Info SCL Release 13 | US | E2E | 102 | 102 | 100 | 100% | ≥99% | Yes | 2025-05-25 | 2025-11-20
DP | Case Management | DP-006 | DP Release 6 | US | UAT | 172 | 171 | 99.42 | 100% | ≥99% | Yes | 2025-07-12 | 2025-12-20
Info SCL | Closing Report Management | IS-017 | Info SCL Release 17 | Italy | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
DP | Connect (Screening & Qualification) & inFO | DP-024 | DP Release 24 | Spain | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
Info SCL | Connect (Sourcing) & inFO | IS-017 | Info SCL Release 17 | US | Regression | 75 | 74 | 98.67 | 100% | ≥99% | No | 2025-04-15 | 2025-10-10
DP | Contact - Candidate Consent (GDPR) | DP-016 | DP Release 16 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Contact - Candidate Management | IS-013 | Info SCL Release 13 | Italy | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
DP | Contact - Candidate Skill Management | DP-014 | DP Release 14 | US | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
DP | Contact - Candidate Unavailability | DP-006 | DP Release 6 | Italy | E2E | 100 | 100 | 100 | 100% | ≥99% | Yes | 2025-04-23 | 2025-10-25
DP | Contact - Client Consent (GDPR) | DP-010 | DP Release 10 | US | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
DP | Contact - Client Management | DP-020 | DP Release 20 | Spain | SIT | 79 | 77 | 97.47 | 100% | ≥99% | No | 2025-01-25 | 2025-07-22
Info SCL | Employee Management | IS-017 | Info SCL Release 17 | Germany | Regression | 174 | 171 | 98.28 | 100% | ≥99% | No | 2025-06-18 | 2025-12-09
DP | Job - Applicant management (convert/reject) | DP-020 | DP Release 20 | Spain | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
Info SCL | Job - ATS Mass Actions | IS-011 | Info SCL Release 11 | US | Regression | 141 | 140 | 99.29 | 100% | ≥99% | Yes | 2025-02-10 | 2025-08-09
Info SCL | Job - ATS Stages | IS-019 | Info SCL Release 19 | Germany | UAT | 74 | 73 | 98.65 | 100% | ≥99% | No | 2025-02-02 | 2025-07-24
DP | Job - Search Job | DP-022 | DP Release 22 | Spain | SIT | 76 | 74 | 97.37 | 100% | ≥99% | No | 2025-05-01 | 2025-11-02
Info SCL | Job - Skill Management | IS-011 | Info SCL Release 11 | Spain | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
DP | Job - Warranty Management | DP-016 | DP Release 16 | Germany | UAT | 89 | 88 | 98.88 | 100% | ≥99% | No | 2025-03-06 | 2025-08-24
DP | Job Create/Update | DP-018 | DP Release 18 | Germany | SIT | 79 | 77 | 97.47 | 100% | ≥99% | No | 2025-01-25 | 2025-07-22
DP | Job Management & Posting | DP-014 | DP Release 14 | US | E2E | 117 | 116 | 99.15 | 100% | ≥99% | Yes | 2025-03-22 | 2025-09-16
Info SCL | Job Match | IS-011 | Info SCL Release 11 | Spain | Regression | 174 | 171 | 98.28 | 100% | ≥99% | No | 2025-06-18 | 2025-12-09
DP | Job Parser | DP-016 | DP Release 16 | Spain | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
Info SCL | Job Posting | IS-009 | Info SCL Release 9 | Germany | UAT | 193 | 193 | 100 | 100% | ≥99% | Yes | 2025-04-07 | 2025-10-03
Info SCL | Journey Management | IS-011 | Info SCL Release 11 | US | E2E | 123 | 122 | 99.19 | 100% | ≥99% | Yes | 2025-02-18 | 2025-08-13
DP | Lead Management | DP-016 | DP Release 16 | US | Regression | 187 | 184 | 98.4 | 100% | ≥99% | No | 2025-05-17 | 2025-11-17
DP | Office - Portfolio Management/L100 | DP-016 | DP Release 16 | Spain | SIT | 136 | 136 | 100 | 100% | ≥99% | Yes | 2025-02-26 | 2025-08-07
DP | Office Account - Market Player Management | DP-012 | DP Release 12 | Germany | SIT | 66 | 63 | 95.45 | 100% | ≥99% | No | 2025-06-02 | 2025-11-20
Info SCL | Opportunity - Approval Process | IS-015 | Info SCL Release 15 | Italy | SIT | 197 | 196 | 99.49 | 100% | ≥99% | Yes | 2025-07-04 | 2025-12-28
Info SCL | Opportunity Management | IS-013 | Info SCL Release 13 | US | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
Info SCL | Planbition | IS-003 | Info SCL Release 3 | Spain | SIT | 108 | 108 | 100 | 100% | ≥99% | Yes | 2025-03-30 | 2025-09-29
DP | Pre-contract | DP-014 | DP Release 14 | US | UAT | 172 | 171 | 99.42 | 100% | ≥99% | Yes | 2025-07-12 | 2025-12-20
Info SCL | Pre-Contract Management | IS-009 | Info SCL Release 9 | Spain | SIT | 108 | 108 | 100 | 100% | ≥99% | Yes | 2025-03-30 | 2025-09-29
Info SCL | Profile of Interest | IS-005 | Info SCL Release 5 | Germany | Regression | 174 | 167 | 95.98 | 100% | ≥99% | No | 2025-07-20 | 2025-12-28
Info SCL | Quick apply | IS-019 | Info SCL Release 19 | Germany | Regression | 187 | 184 | 98.4 | 100% | ≥99% | No | 2025-05-17 | 2025-11-17
Info SCL | Report and Dashboard | IS-013 | Info SCL Release 13 | Germany | UAT | 186 | 185 | 99.46 | 100% | ≥99% | Yes | 2025-06-10 | 2025-12-08
Info SCL | Resume Parser | IS-019 | Info SCL Release 19 | Italy | E2E | 127 | 126 | 99.21 | 100% | ≥99% | Yes | 2025-06-26 | 2025-12-14
Info SCL | rNPS | IS-009 | Info SCL Release 9 | Italy | Regression | 197 | 195 | 98.98 | 100% | ≥99% | No | 2025-03-14 | 2025-08-23